## Sheet1
ITSC-3155 Software Engineering | [5 empty] | Srinivas | Mihir | Kanaan
Product Backlog
Feature Name | PRIORITY | POINTS | DEFINE USER STORY | ASSIGNED TO SPRINT | SPRINT #
User Registration/Login | High | 8 | Yes | Yes | 1
Guest Checkout | High | 5 | Yes | Yes | 1
Menu Display & Categories | High | 13 | Yes | Yes | 1
Add to Cart Functionality | High | 8 | Yes | Yes | 1
Order Placement (Delivery/Takeout) | High | 13 | Yes | Yes | 2
Payment Integration (Multiple Methods) | High | 13 | Yes | Yes | 2
Order Tracking (Real-Time Status) | High | 8 | Yes | Yes | 2
Admin Dashboard (Manage Orders/Menu) | Medium | 13 | Yes | Yes | 3
Chef/Staff Order View | Medium | 8 | Yes | Yes | 3
Reviews & Ratings System | Medium | 5 | Yes | No | 3
Promo Codes & Discounts | Medium | 8 | Yes | No | 4
Notifications (Order Updates) | Medium | 5 | Yes | No | 4
Data Analytics Dashboard | Low | 13 | Yes | No | 4
Customer Order History | Low | 5 | Yes | No | 4
Documentation & Training Module | Low | 3 | No | No | 4