## use both sprint review 1 and 2
Story Tasks | Story Point | Assigned to | Estimated Effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
Sprint 1 User Story 1 Basic setup & Database | 8 |  | 15 | 5 | 5 | 5 | 0 | 0 | 0 | Done
Task Initialize FastAPI app and folder structure |  | Mihir | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Done
Task Set up MySQL database connection |  | Kanaan | 6 | 1 | 5 | 0 | 0 | 0 | 0 | Done
Task Create base models and Pydantic schemas |  | Srinivas | 5 | 0 | 0 | 5 | 0 | 0 | 0 | Done
Sprint 1 User Story 2 Manage the sandwich menu | 13 |  | 20 | 0 | 4 | 6 | 6 | 4 | 0 | Done
Task Create Sandwich database model and schemas |  | Mihir | 4 | 0 | 4 | 0 | 0 | 0 | 0 | Done
Task Implement POST sandwiches endpoint |  | Kanaan | 5 | 0 | 0 | 5 | 0 | 0 | 0 | Done
Task Implement GET sandwiches endpoints |  | Srinivas | 5 | 0 | 0 | 1 | 4 | 0 | 0 | Done
Task Implement PUT and DELETE sandwiches endpoints |  | Mihir | 6 | 0 | 0 | 0 | 2 | 4 | 0 | Done
Sprint 1 User Story 3 Create customer orders | 5 |  | 12 | 0 | 0 | 0 | 4 | 5 | 3 | Done
Task Create Order model and schemas |  | Kanaan | 4 | 0 | 0 | 0 | 4 | 0 | 0 | Done
Task Implement POST orders endpoint |  | Srinivas | 5 | 0 | 0 | 0 | 0 | 5 | 0 | Done
Task Implement GET orders endpoints |  | Mihir | 3 | 0 | 0 | 0 | 0 | 0 | 3 | Done
Sprint 2 User Story 4 Manage Resources & Recipes | 8 |  | 16 | 6 | 5 | 5 | 0 | 0 | 0 | Done
Task Create Resource model and schemas |  | Kanaan | 6 | 6 | 0 | 0 | 0 | 0 | 0 | Done
Task Implement endpoints for resources |  | Srinivas | 5 | 0 | 5 | 0 | 0 | 0 | 0 | Done
Task Implement recipes endpoint to link data |  | Mihir | 5 | 0 | 0 | 5 | 0 | 0 | 0 | Done
Sprint 2 User Story 5 Connect Order Details | 13 |  | 18 | 0 | 4 | 6 | 8 | 0 | 0 | Done
Task Create OrderDetail model to link tables |  | Kanaan | 5 | 0 | 4 | 1 | 0 | 0 | 0 | Done
Task Implement POST order details endpoint |  | Srinivas | 5 | 0 | 0 | 5 | 0 | 0 | 0 | Done
Task Resolve SQLAlchemy table collisions |  | Mihir | 8 | 0 | 0 | 0 | 8 | 0 | 0 | Done
Sprint 2 User Story 6 Unit Testing & Integration | 5 |  | 15 | 0 | 0 | 0 | 3 | 8 | 4 | Done
Task Fix router connection 404 errors in main |  | Kanaan | 4 | 0 | 0 | 0 | 3 | 1 | 0 | Done
Task Write and execute pytest for all endpoints |  | Srinivas | 8 | 0 | 0 | 0 | 0 | 7 | 1 | Done
Task Ensure correct response codes across endpoints |  | Mihir | 3 | 0 | 0 | 0 | 0 | 0 | 3 | Done